## Slide 1: Class 2DI2DJ Group 087 SPRINT 2
Group members:
FRANCISCA ROMANO DA CUNHA MORAIS (1181122)
JOÃO SOARES MARQUES (11922210)
PAULO TIAGO FERREIRA COUTO (1200587)
TIAGO MOISÉS SAMPAIO DA SILVA (1191938)

## Slide 2: Sprint planning – Sprint 2
SPRINT BACKLOG | 
Number of stories | 20
Number of bugs | 0
Number of tasks | 5
Number of Management Tasks | 3
Number of team members | Planned: 6 Actual: 6
Total planned estimation vs execution | Planned hours: 56 Executed hours:110
Planned Start Date: 15/11/2021 Real Start Date: 18/11/2021
Planned Finished Date: 03/12/2021 Real Finish Date:06/12/2021

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 301 | YES |  |  |  | X | 
US 302 | YES |  |  |  | X | 
US 303 | YES |  |  |  | X | 
US 304 | YES |  |  |  | X | 
US 305 | YES |  |  |  | X | 
US 306 | YES |  |  |  | X | 
US 307 | YES |  |  |  | X | 
US 308 | YES |  |  |  | X | 
US 309 | YES |  |  |  | X | 
US 310 | YES |  |  |  |  | 
US 311 | NO |  |  |  |  | 
US312 |  |  |  |  |  | 

## Slide 4: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 313 | YES |  |  |  | X | 
US 314 | YES |  |  |  | X | 
US 315 | YES |  |  |  | X | 
US 316 | YES |  |  |  | X | 
US 317 | YES |  |  |  | X | 
US 318 | YES |  |  |  | X | 
US 319 | YES |  |  |  | X | 
US 320 | YES |  |  |  | X | 
 |  |  |  |  | X | 

## Slide 5: Sprint Execution
Issues | Sprint Backlog (a) | Added issues during sprint (b) | Closed issues from initial planning (c) | Closed issues from added ones (d) | Issues not closed (e) | % Execution | 
 |  |  |  |  |  | Planned (c/a) | Total (c+d)/(a+b)
Number of stories (I) | 20 | 0 | 19 | 0 | 0 | 95% | 96%
Number of bugs (II) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Number of tasks (III) | 0 | 5 | 0 | 5 | 0 | 0 | 100%
TOTAL | 20 | 5 | 19 | 5 | 0 | 95 | 96%
Total Estimate | 48h | 8h | 24h | 6h | 4h | 50% | 50%

## Slide 6: Work by team member
Chart: Hours / n. tasks
| 1191938 | 1200587 | 1192221 | 1181122
Horas / tarefas | 4.2 | 3.8 | 4 | 3.5

## Slide 7: Work by type
Chart: Componente

## Slide 8: Sprint Burndown Chart
Print do JIRA após fecho da sprint

## Slide 9: Sprint Review
Date: 05/12/2021
Main conclusions:
Missing Esinf
Not sure how BDDAD is because database stopped working by the end
Arqcp not working
FISIAP all done
Start early

## Slide 10: Sprint Retrospective
Date:
What went well?
Work distribution
What went wrong?
We started really late
What we’ve learned?
We need to start earlier because we have no time if something goes wrong

## Slide 11: Sprint Retrospective
Date: 05/12/2021
Action items:
What went well: Communication and response to change
What went wrong: Sprint start
What will we do different next sprint: Start earlier

## Slide 12: Team performance metrics