## Slide 1: Class 2DI2DJ Group 087 SPRINT 2
Group members:
FRANCISCA ROMANO DA CUNHA MORAIS (1181122)
JOÃO SOARES MARQUES (11922210)
PAULO TIAGO FERREIRA COUTO (1200587)
TIAGO MOISÉS SAMPAIO DA SILVA (1191938)

## Slide 2: Sprint planning – Sprint 2
SPRINT BACKLOG | 
Number of stories | 12
Number of bugs | 0
Number of tasks | 4
Number of Management Tasks | 1
Number of team members | Planned: 6 Actual: 6
Total planned estimation vs execution | Planned hours: 120 Executed hours:110
Planned Start Date: 15/11/2021 Real Start Date: 18/11/2021
Planned Finished Date: 03/12/2021 Real Finish Date:06/12/2021

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US 201 | YES |  |  |  | X | 
US 202 | YES |  |  |  | X | 
US 203 | YES |  |  |  | X | 
US 204 | YES |  |  |  | X | 
US 205 | YES |  |  |  | X | 
US 206 | YES |  |  |  | X | 
US 207 | YES |  |  |  | X | 
US 208 | YES |  |  |  | X | 
US 209 | YES |  |  |  | X | 
US 210 | NO |  |  |  |  | X

## Slide 4: Sprint Execution
Issues | Sprint Backlog (a) | Added issues during sprint (b) | Closed issues from initial planning (c) | Closed issues from added ones (d) | Issues not closed (e) | % Execution | 
 |  |  |  |  |  | Planned (c/a) | Total (c+d)/(a+b)
Number of stories (I) | 10 | 2 | 9 | 2 | 1 | 5 | 92%
Number of bugs (II) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Number of tasks (III) | 0 | 4 | 0 | 4 | 0 | 0 | 100%
TOTAL | 10 | 6 | 0 | 6 | 1 | 5 | 92%
Total Estimate | 120h | 10h | 110h | 9h | 4h | 92% | 0,91%

## Slide 5: Work by team member
Chart: Hours / n. tasks
| 1191938 | 1200587 | 1192221 | 1181122
Horas / tarefas | 4.2 | 3.8 | 4 | 3.5

## Slide 6: Work by type
Chart: Componente

## Slide 7: Sprint Burndown Chart
Print do JIRA após fecho da sprint

## Slide 8: Sprint Review
Date: 05/12/2021
Main conclusions:
Esinf all done with no errors
Bdad couldn’t do US210
We started late because of exams, other works and logical model review
Mutation could be improved

## Slide 9: Sprint Retrospective
Date:
What went well?
Communication
Work distribution
What went wrong?
Estimated times
One user story
What we’ve learned?
How to estimate time better
Log our work

## Slide 10: Sprint Retrospective
Date: 05/12/2021
Action items:
What went well: Communication and response to change
What went wrong: Daily meetings aren´t logged properly. Estimate times.
What will we do different next sprint: Estimate better the user stories. Log the meeting and our work better.

## Slide 11: Team performance metrics